BURGER KING INDONESIA

First Loyalty Program Launch

Part 1 of 5  —  Marketing Brief

Prepared by: Kitty Rastogi  |  Role: Product & Growth Marketing  |  2023

"This wasn't just a loyalty feature launch. It was a multi-year investment to shift consumer behavior, reduce coupon dependency, and build a sustainable engine for customer lifetime value."

1. Business Context & Opportunity

Background

Burger King Indonesia's mobile app had been live for 3–4 years. App downloads were growing steadily and customer acquisition remained strong. However, retention lagged 30–40% below target, and repeat purchase behavior was heavily dependent on short-term promotions and coupon campaigns.

Competitors — McDonald's, KFC, and Starbucks — had already established well-performing loyalty programs that were visibly driving repeat visits and engagement. This validated that the Indonesian market was ready for a loyalty-led retention strategy.

| Signal | Implication |
| --- | --- |
| App downloads strong, retention weak | Acquisition wasn't the problem — we needed a retention engine |
| 30–40% below retention target | Status quo (coupons + promotions) was not a sustainable strategy |
| Competitors had live loyalty programs | Market timing was right; further delay was a competitive risk |
| Users were promotion-driven | Behavior change was needed — not just another short-term campaign |

Strategic Framing

From the outset, this program was framed as a long-term business investment — not a marketing campaign. The opportunity was to:

- Shift Burger King from a coupon-heavy, promotion-dependent brand to a loyalty-driven business

- Build a sustainable retention engine capable of increasing Customer Lifetime Value (CLV)

- Create a program that could drive ~20% of revenue through loyalty-linked transactions within 3 years

- Reduce reliance on discounting as the primary lever for customer engagement

The goal wasn't to launch a feature. It was to build a long-term growth engine that could durably change how customers engaged with Burger King.

2. Program Objectives & Success Metrics

Phased Goal Framework

To align Finance, Marketing, Product, and Operations stakeholders, I built a phased investment model tied to measurable business outcomes. This gave stakeholders a clear view of both near-term launch expectations and long-term return on investment.

| Horizon | Goal | Success Metric |
| --- | --- | --- |
| 6 Months (Launch Phase) | Drive rapid adoption and validate redemption behavior | 40% loyalty adoption among MAUs 50–70% first redemption rate 10% revenue lift |
| 12 Months (Growth Phase) | Improve retention and reduce promotion dependency | 9% improvement in 90-day repeat purchase rate YoY Reduced discount-led CRM spend |
| 3 Years (Transformation) | Shift BK from promotion-led to loyalty-driven business | ~20% of revenue through loyalty-linked transactions Sustainable CLV growth without constant discounting |

3. Target Audience

Primary Segments

I worked with the Analytics team to segment the existing user base and identify which cohorts had the highest potential for loyalty adoption and long-term value.

| Segment | Profile | Why They Matter |
| --- | --- | --- |
| Students | 18–24 years old, high purchase frequency, digitally native, price-sensitive, socially active on TikTok and Instagram | Highest purchase frequency relative to spend, most responsive to reward-based engagement, strong word-of-mouth multiplier |
| Repeat App Users | Customers with 2–4 purchases/month, already engaged with the app, coupon users | Easiest to convert to loyalty — already have app habit, need a reason to return without a coupon |
| Lapsed Users | Downloaded app, made 1–2 purchases, then dropped off | Re-engagement opportunity — loyalty benefits as a re-activation hook |

Primary Target for Launch

Students and repeat app users were identified as the primary launch targets. Students for frequency and social amplification; repeat users for conversion efficiency and near-term retention impact.

4. Budget Phasing Framework

Methodology

I built the budget using a target-based methodology — working backwards from adoption, redemption, and revenue goals rather than starting from a fixed spend pool. This ensured resource allocation was tied to outcomes rather than historical precedent.

| Phase | Investment Rationale |
| --- | --- |
| Launch Phase (Months 1–6) | Heaviest investment period. Spend concentrated on adoption, education, and channel activation. Push notifications, TikTok influencer campaigns, in-store QR code rollout, fintech/CPG partnership activations, and CRM onboarding sequences all ran simultaneously. |
| Sustenance Phase (Months 7–12) | Lighter maintenance spend. Focus shifts from acquisition to engagement and retention. CRM-led re-engagement, loyalty milestone rewards, personalized push campaigns for at-risk segments. |
| Seasonal Spikes (Ongoing) | Incremental budget allocated to Ramadan and major holidays — peak purchase intent windows. Loyalty-linked promotions designed to accelerate point earning and boost redemption during high-traffic periods. |

Budget approval was secured through alignment sessions with Finance, Marketing, and Operations — with sign-off from each function before launch was greenlit.

5. Stakeholders & Roles

| Team | Role in Program | Key Dependency |
| --- | --- | --- |
| Product & Engineering | App integration, loyalty earn/redeem mechanics, onboarding flow, in-app visibility | Feature readiness timeline, beta testing support |
| Marketing & CRM | Channel execution, push notifications, email campaigns, influencer partnerships | Messaging alignment, campaign calendar coordination |
| Finance | Budget approval, P&L modeling, ROI tracking | Phased investment sign-off, revenue uplift reporting |
| Operations & Store Teams | In-store QR code deployment, menu board updates, staff education | Physical activation readiness before launch |
| Supply Chain | Reward redemption inventory planning | Ensure reward items available at point of redemption |
| Analytics | Customer segmentation, KPI dashboards, cohort analysis | Data infrastructure for loyalty tracking from day one |

Burger King Indonesia — Loyalty Program Marketing Brief  |  PMM Work Sample  |  Kitty Rastogi